## Slide 1: Strategic Plan Update
Q2 Academic Year 2017-18 (September 2017 – December 2017)

## Slide 2: Year 3 Initiatives
Enrollment
  Deliver Strategic Enrollment Plan by December 2017
  Deliver Academic Master Plan by April 2018
  Deliver new intentional advising and student success model and system serving at least 2,400 first- and second-year students per year – beginning in Fall 2017
  Deliver proposals for four new degree programs in FY2018
  Deliver Strategic Technology Plan by April 2018
Strengthen Governance & Foster Community
  Deliver Leadership Training Program for 50 employee participants by Spring 2018
  Deliver better internal communications with
    Monthly face-to-face institution-wide directors’ meeting starting September 2017
    New Intranet by March 2018
Leverage Resources & Increase Revenue
  Deliver outreach to secure diversified revenue:
    Continue first Capital Campaign in a decade
      12% increase in fundraising for needs-based scholarships in FY18 over FY17
      Secure multi-million-dollar gift to fund a center to help first-generation students
    Launch grant writing infrastructure
    Seek funding from the 2018 General Assembly for FY19
      $1.8 million to support sector change
      $4.9 million for statewide aviation growth
      $12.7 million for major capital improvements in Cochran
Enhance Service to Students
  Deliver 75% of Student Affairs programming aligned to Student Engagement model
    Guide 100 students to Bronze certification in Experiential Learning
  Deliver Comprehensive Housing Plan wi9th alternatives to P3 and living-learning communities for implementation and launch in Fall 2018

## Slide 3: Year 3 Initiatives Progress
Chart: Percent Complete
| 10) Comprehensive Housing Plan | 9b) 100 Bronze-level EL Certifications | 9a) Student Affairs Programming Aligned to Student Engagement Model | 8c) Diversified Revenue - General Assembly Funding | 8b) Diversified Revenue - Grant Infrastructure | 8a) Diversified Revenue - Capital Campaign | 7b) Better Internal Communcations - Intranet | 7) Better Internal Communications - Face to Face | 6) Leadership Training | 5) Strategic Technology Plan | 4) New Programs | 3) Advising System | 2) Academic Master Plan | 1) Strategic Enrollment Plan
Percent Complete | 80 | 50 | 100 | 50 | 50 | 50 | 80 | 100 | 50 | 30 | 50 | 50 | 25 | 65

## Slide 4: Detailed Updates

## Slide 5: Progress in Focus on Enrollment
Chart: Percent Complete
| 5) Strategic Technology Plan | 4) New Programs | 3) Advising System | 2) Academic Master Plan | 1) Strategic Enrollment Plan
Percent Complete | 30 | 50 | 50 | 25 | 65
Enrollment Action Plan moving forward. Marketing research, demand analysis, and meta-analysis of consultant reports underway and pending the arrival of new Provost.
Analysis of programming available on the Cochran Campus complete with projection of additions to the Cochran academic portfolio through 2019. Deans identifying which programs are fully available on each campus.
Model crafted in 2017 being evaluated and refined for implementation in 2018, pending approval by new Provost.
Proposal for BS in Political Science to be delivered to Cochran campus submitted to USG. Proposal for MS in Social Work to be delivered on the Macon campus submitted to USG. Administrative approval for AS in Health Science was granted by USG.
Meeting with Academic units. Will also work closely with new Provost upon arrival.

## Slide 6: Progress on Strengthen Governance & Foster Community
Chart: Percent Complete
| 7b) Better Internal Communcations - Intranet | 7a) Better Internal Communications - Face to Face | 6) Leadership Training
Percent Complete | 80 | 100 | 50
25 employees were selected for and began Leadership training in Fall 2017. Another 25 will receive training in interviewing in Spring 2018.
a) Monthly face to face meetings among directors across all units began in October.
b) Prototype designed and developed. Soon to meet with Marketing & Communications to further discuss the look. Intranet should go to test users in January.

## Slide 7: Progress on Diversified Revenue
Chart: Percent Complete
| 8c) Diversified Revenue - General Assembly funding | 8b) Diversified Revenue - Grant Infrastructure | 8a) Diversified Revenue - Capital Campaign
Percent Complete | 50 | 50 | 40
a) Approximately 13% increase obtained in need-based scholarship funds awarded. Proposal for multi-million-dollar gift is being drafted for presentation in April 2018 to potential funders.
b) Acquired and installed grant lead software. Created and staffing grant writer position. Candidate interviews underway.
c) Requesting $1,895,400 in sector change and enrollment funding in October as a part of the USG Budget Hearing process in January. Also making the case to the USG for an additional $1,425,000 in Graduate Programs/Year of Momentum and Retention/Enrollment funding. We will find out how much funding we receive with the Budget Allocations in April.

## Slide 8: Progress on Enhance Service to Students
Chart: Percent Complete
| 10) Comprehensive Housing Plan | 9b) 100 Bronze-level EL Certifications | 9a) Student Affairs Programming Aligned to Student Engagement Model
Percent Complete | 80 | 50 | 100
a) The number of programs provided from July 2017 – December 2017 for each of the categories of the Student Engagement model.
  Life skills – 223
  Wellness – 183
  Service learning – 16
  Community building – 154
  Diversity – 39
  Scholarship – 30
9) b) The number of students who have received the following certifications due to Student Affairs programs/events:
  Bronze – 34
  Silver – 4
  Gold – 3
  Platinum - 1
The written housing plan is complete. Details for the living learning communities are still being worked on.